## Sheet1
Berlin ADA Transition Plan 3-2023
Facility |  | Problem | Solution | Timeframe/Completion
Town Hall | 1 | Do all inaccessible entrances have signs indicating the locations of the nearest accessible entrance? | Install signs before inaccessible entrances so that people do not have to retrace the approach. | Completed
Town Hall | 2 | If provided, do signs and room numbers designating permanent rooms and spaces where goods and services are provided comply with the appropriate requirements for such signage? | Provide signs that have raised letters, Grade II Braille, and that meet all other requirements for permanent room or space signage. | Completed
Town Hall
Town Hall | 3 | Do directional and informational signs comply with legibility requirements? | Review requirements and replace signs as needed. | Completed
Town Hall
Town Hall | 4 | At each type of cashier counter, is there a portion of the main counter that is not more than 36 inches high? | Provide a lower auxiliary counter or folding shelf. | Completed
Town Hall
Town Hall | 5 | If restrooms are available to the public, is at least one restroom (either one for each sex, or unisex) fully accessible? | Reconfigure restroom. | See item 14 Town Hall
Town Hall
Town Hall | 6 | Are there signs at inaccessible restrooms that give directions to accessible ones? | Install accessible signs. | Completed
Town Hall
Town Hall | 7 | Are pictograms or symbols used to identify restrooms, and, if used, are raised characters and Braille included below them? | If symbols are used, add supplementary verbal signage with raised characters and Braille below pictogram symbol. | 4 Weeks – Completed 7/1/13
Town Hall
Town Hall | 8 | Is there a wheelchair-accessible stall that has an area of at least 5 feet by 5 feet, clear of the door swing, OR is there a stall that is less accessible but that provides greater access than a typical stall (either 36 by 69 inches or 48 by 69 inches)? | Move or remove partitions. | See item 14 Town Hall
Town Hall
Town Hall | 9 | In the accessible stall, are there grab bars behind and the sidewall nearest to the toilet? | Add grab bars. | Completed
Town Hall | 10 | Is there at least 29 inches from the floor to the bottom of the lavatory apron (excluding pipes)? | Adjust or replace lavatory | See item 14 Town Hall
Town Hall
Town Hall | 11 | Is the mirror mounted with the bottom edge of the reflecting surface 40 inches high or lower? | Lower or tilt down the mirror. | Completed
Town Hall | 12 | Is there one fountain with its spout no higher than 36 inches from the ground, and another with a standard height spout (or a single high-lo fountain)? | Provide cup dispensers for fountains with spouts that are too high. Provide accessible cooler. | 1 Year
Town Hall | 13 | Hire a professional architect to review ADA requirements for Town buildings and obtain a report to help identify deficiencies and update transition plan. | Hire architect and complete report | Completed
Town Hall | 14 | Provide minimum of one accessible toilet per ANSI requirements to comply with ANSI per recommendation in Friar Report, 2017 and make other improvements in restrooms as recommended in Friar Report. | Adjust or replace lavatory | 2 Years
Town Hall | 15 | Provide handrails on both sides of hallway to meet ANSI to comply with ANSI per recommendation in Friar Report, 2017. | Install handrails | 3 Years
Town Hall | 16 | Provide call for aid system in restrooms to comply with ANSI per recommendation in Friar Report, 2017. | Provide call for aid system | 2 Years
Town Hall | 17 | Designate accessible parking location, provide proper signage drop-off area and access to the site via an accessible route. Identified in 2017 report from Friar Architects. | Modify parking/drop off area. | Completed
Town Hall | 18 | Rework ramp at main entrance. Provide ramp compliant ramp including but not limited to proper landings, handrails, signage, etc. Per recommendation in Friar Report, 2017. | Rework ramp at main entrance. | Completed
Town Hall | 19 | Provide second accessible means of egress per recommendation in Friar Report, 2017. | Construct second means of egress. | 1 year
Town Hall | 20 | Replace door hardware to comply with ANSI per recommendation in Friar Report, 2017. | Replace door hardware. | Completed
Town Hall | 21 | Replace doors to comply with ANSI per recommendation in Friar Report, 2017. | Replace doors. | Completed 1 power assisted entry door in 2019, two scheduled for installation in 2021.
Town Hall | 22 | Provide interior and exterior signage for compliance along accessible route to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify interior and exterior signage. | Completed
Town Hall | 23 | Provide accessible drinking fountain with required clear floor space to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify drinking fountain. | 4 Years
Town Hall | 24 | Provide knee/toe clearance and clear floor space at sinks to comply with ANSI per recommendation in Friar Report, 2017. | Modify sinks | 4 Years
Town Hall | 25 | Provide tactile warning throughout to comply with ANSI per recommendation in Friar Report, 2017. | Install tactile warnings. | 1 Year
Town Hall | 26 | Provide an area of rescue assistance to comply with ANSI per recommendation in Friar Report, 2017. | Construct area of rescue. | 5 years
Facility |  | Problem | Install accessible elevator. | Timeframe
Library/Community Center | 1 | Do all inaccessible entrances have signs indicating the location of the nearest accessible entrance? | Install signs before inaccessible entrances so that people do not have to retrace the approach. | Completed
Library/Community Center | 2 | If provided, do signs and room numbers designating permanent rooms and spaces where goods and services are provided comply with the appropriate requirements for such signage? | Provide signs that have raised letters, Grade II Braille, and that meet all other requirements for permanent room or space signage. | Completed (Jan 2023)
Library/Community Center | 3 | In the accessible stall, are there grab bars behind and on the side wall nearest to the toilet? | Add grab bars | Completed
Library/Community Center | 4 | Is there at least 29 inches from the floor to the bottom of the lavatory apron (excluding pipes)? | Adjust or replace lavatory | See Berlin Peck Memorial Library item 5
Library/Community Center | 5 | Provide minimum of one accessible toilet per ANSI requirements to comply with ANSI per recommendation in Friar Report, 2017 and make other improvements in restrooms as recommended in Friar Report. | Adjust or replace lavatory | 2 Years
Library/Community Center | 6 | Provide handrails on both sides of hallway to comply with ANSI per recommendation in Friar Report, 2017. | Install handrails | 3 Years
Library/Community Center | 7 | Provide call for aid system to comply with ANSI per recommendation in Friar Report, 2017. | Provide call for aid system | 2 Years
Library/Community Center | 8 | Designate accessible parking location, provide proper signage drop-off area and access to the site via an accessible route. Identified in 2017 report from Friar Architects. | Modify parking/drop off area. | Completed
Library/Community Center | 9 | Provide ramp compliant ramp including but not limited to proper landings, handrails, signage, etc. Per recommendation in Friar Report, 2017. | Rework ramp at main entrance. | Completed
Library/Community Center | 10 | Provide second accessible means of egress per recommendation in Friar Report, 2017. | Construct second means of egress. | 5 Years
Library/Community Center | 11 | Replace door hardware to comply with ANSI per recommendation in Friar Report, 2017. | Replace door hardware. | 3 Years
Library/Community Center | 12 | Replace doors to comply with ANSI per recommendation in Friar Report, 2017. | Replace doors. | 3 Years
Library/Community Center | 13 | Provide interior and exterior signage for compliance along accessible route to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify interior and exterior signage. | 1 Year
Library/Community Center | 14 | Provide accessible drinking fountain with required clear floor space to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify drinking fountain. | 4 Years
Library/Community Center | 15 | Provide knee/toe clearance and clear floor space at sinks to comply with ANSI per recommendation in Friar Report, 2017. | Modify sinks | 4 Years
Library/Community Center | 16 | Provide tactile warning throughout to comply with ANSI per recommendation in Friar Report, 2017. | Install tactile warnings. | 1 Year
Library/Community Center | 17 | Provide an area of rescue assistance to comply with ANSI per recommendation in Friar Report, 2017. | Construct area of rescue. | 5 Years
Library/Community Center | 18 | Provide second accessible means of egress (ramp) from Library Meeting Room to exterior walkway to comply with ANSI per recommendation in Friar Report, 2017. | Construct second means of egress. | 5 Years
Library/Community Center | 19 | Install a new accessible elevator for access for the Library and Community Center. | Install accessible elevator. | Completed
Facility |  | Problem | Solution | Timeframe
Senior Center | 1 | Do all inaccessible entrances have signs indicating the locations of the nearest accessible entrance? | Install signs before inaccessible entrances so that people do not have to retrace the approach. | Completed
Senior Center | 2 | If mounted above 80 inches, do they have letters at least 3 inches high, with high contrast, and non-glare finish? | Review requirements and replace signs as needed, meeting the requirements for character size, contrast and finish. | 1 Year
Senior Center | 3 | Do directional and informational signs comply with legibility requirements? | Review requirements and replace signs as needed. | Completed
Senior Center | 4 | In the accessible stall, are there grab bars behind and on the side wall nearest to the toilet? | Add grab bars | Completed
Senior Center | 5 | Provide minimum of one accessible toilet per ANSI requirements to comply with ANSI per recommendation in Friar Report, 2017 and make other improvements in restrooms as recommended in Friar Report. | Adjust or replace lavatory | 1 Year
Senior Center | 6 | Provide handrails on both sides of hallway to comply with ANSI per recommendation in Friar Report, 2017. | Install handrails | 3 Years
Senior Center | 7 | Provide call for aid system to comply with ANSI per recommendation in Friar Report, 2017. | Provide call for aid system | Completed
Senior Center | 8 | Designate accessible parking location, provide proper signage drop-off area and access to the site via an accessible route. Identified in 2017 report from Friar Architects. | Completed | Completed
Senior Center | 9 | Provide ramp compliant ramp including but not limited to proper landings, handrails, signage, etc. Per recommendation in Friar Report, 2017. | Rework ramp at main entrance. | Completed
Senior Center | 10 | Provide second accessible means of egress per recommendation in Friar Report, 2017. | Construct second means of egress. | 3 Years
Senior Center | 11 | Replace door hardware to comply with ANSI per recommendation in Friar Report, 2017. | Replace door hardware. | Completed
Senior Center | 12 | Replace doors to comply with ANSI per recommendation in Friar Report, 2017. | Replace doors. | Updated 1 power assisted entry door and installed per assisted doors in rest rooms in 2019. Other doors - 3 Years
Senior Center | 13 | Provide interior and exterior signage for compliance along accessible route to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify interior and exterior signage. | 1 Year
Senior Center | 14 | Provide accessible drinking fountain with required clear floor space to comply with ANSI per recommendation in Friar Report, 2017. | Install/modify drinking fountain. | 4 Years
Senior Center | 15 | Provide knee/toe clearance and clear floor space at sinks to comply with ANSI per recommendation in Friar Report, 2017. | Modify sinks | 4 Years
Senior Center | 16 | Provide tactile warning throughout to comply with ANSI per recommendation in Friar Report, 2017. | Install tactile warnings. | 1 Year
Senior Center | 17 | Provide an area of rescue assistance to comply with ANSI per recommendation in Friar Report, 2017. | Construct area of rescue. | 5 Years
Senior Center | 18 | Provide second accessible means of egress (ramp) from Multi-Purpose Room to exterior walkway to comply with ANSI per recommendation in Friar Report, 2017. | Construct second means of egress. | 5 Years
Senior Center | 19 | Provide access to platform in Multi-Purpose to comply with ANSI per recommendation in Friar Report, 2017. | Construct access to platform. | 5 Years